## Sheet1
EVENT PREPARATION CHECKLIST
| STAFF MEMBER | TASK COMPLETE | NOTES
3-4 MONTHS OUT
Confirm Date & Book Venue (plus any AV required)
If on-site accomodation required book now as part of Venue Package
If hosting an onsite Dinner/Party book now as part of Venue Package
Diarise when the venue installment payments are due
Email RSVP to Students
Order any event supplies that have extended waiting periods eg. custom journals etc
6 WEEKS OUT
Select any games/activities you wish to run in line with the content
Drum up RSVP's - FB, messages etc
4 WEEKS OUT
RSVP's due - chase up and finalise
If having an off-site Dinner/Party book now
Any books or gifts ordered to allow for delays
Gift bags ordered
If doing table decorations organise, buy/order
Put together a shopping list and make purchases |  |  | Use both this list and packing list as a reference to what you may need. Remember anything that comes up last minute can be purchased later this just saves time.
Start creating workbook content (the sooner complete the better)
Any students having a Birthday - organise cake etc
3 WEEKS OUT
Send 'What to Expect Email' inc Student homework if applicable
Print event T&C's on clipboards ready to be signed
Print order forms to bring for upgrades/sales
Print attendees emergency contact list
2 WEEKS OUT
Triple check and confirm everything with the event venue
Typically menu selections will be due with event venue plus dietary requirements/allergies
Typically final numbers will be due with event venue |  |  | Depending on the venue if you have a student start after this point you may be able to convince them to add extras numbers on but you won't be able to drop numbers
Complete workbook content (at the absolute latest) |  |  | This allows printing and re-printing time particularly if you are using an off-site prining service
Print and bind workbook (at the latest) |  |  | Print a bound copy for yourself and any staff plus bring an unbound copy as spare pages if required by a student
1 WEEK OUT
Start making a pile of everything you need to pack in one place as it is complete and ready to go
Your runsheet completed
Music playlist created from workbook
Powerpoint created from workbook
Print name badges/lanyards
Put together a seating plan (if applicable) |  |  | Print the seating plan for people to find their seats plus another one for you in your paperwork to assist in putting names to faces
Print place card settings (if applicable)
Attendance list printed to be checked off
Save all workbooks/worksheets and event docs to an 'Event USB' as backup
Print all event venue documents |  |  | In case you need cross check any issues while you are there - it is a lot faster than trawling through emails searching.
Facebook post about how excited you are and any relevant last minute updates/info eg.weather |  |  | This can't be set up in FB scheduler too far in advance due to weather etc
3 DAYS BEFORE
Schedule vacation responder on your email
Add start and finish times, break times etc to your phone calendar
Schedule posts for registration time and location each day
Test logins etc of your online terminal/physical terminal ready to go
DAY BEFORE
Change voicemail if required
Facebook post about starting time tomorrow and anything they need to bring with them etc |  |  | This can be set up in FB scheduler in advance if you wish
DAY OF
AV Check
Put gift bags together ready to hand out or on tables |  |  | This can be done in advance if you have the space to transport them this way without damage
Music on outside to create a positive atmosphere
Register/Mark off attendees
Hand out and retrieve signed forms (mark off too)
POST-BOOTCAMP
Student check-in calls |  |  | 3 days post-event
Provide any feedback to the venue
Check final invoice from venue (if applicable)
Schedule any FB posts related to the event that you told students you would check in on them about (eg. experiencing joy photos)